CALL FOR PROPOSALS Youth Climate Justice Micro-Grant Program Arab Youth Sustainable Development Network (AYSDN) Funded by the Youth Climate Justice Fund (YCJF) CFP Ref: YCJF-YEM-CFP-2026 │ Yemen │ Jun – Aug 2026 Proposal Submission Deadline: July 28, 2026

| 5 Grants Available | $500 Per Grant (USD) | $2,500 Total Envelope | 3 Thematic Pillars |
| --- | --- | --- | --- |

1.  INTRODUCTION & BACKGROUND

The Arab Youth Sustainable Development Network (AYSDN) invites qualified individual youth and youth-led organizations in Yemen to submit proposals under the Youth Climate Justice Micro-Grant Program. This Call for Proposals (CFP) is issued under CFP Reference YCJF-YEM-CFP-2026 and forms part of AYSDN's sub-grant commitment within the Youth Climate Justice Fund (YCJF).

Yemen is among the world's most climate-vulnerable countries, with communities disproportionately affected by drought, flooding, food insecurity, and displacement. Young people are both primary victims of this crisis and indispensable agents of locally-driven solutions. This program seeks to unlock that potential by providing direct financial support to youth-led climate initiatives across three thematic pillars.

| Issuing Organization | Arab Youth Sustainable Development Network (AYSDN) |
| --- | --- |

| Funding Source | Youth Climate Justice Fund (YCJF) |
| --- | --- |

| CFP Reference | YCJF-YEM-CFP-2026 |
| --- | --- |

| Geographic Focus | Yemen — all governorates |
| --- | --- |

| Program Period | June 2026 – June 2027 (Implementation: Sep 2026 – Mar 2027) |
| --- | --- |

| Submission Deadline | July 28, 2026 at 23:59 Yemen Time (YT) |
| --- | --- |

2.  PROGRAM OBJECTIVES

This CFP seeks to fund youth-led proposals that contribute to the following objectives:

- Strengthen the capacity of young climate leaders in Yemen to design and implement impactful environmental initiatives

- Support community-based climate action with direct, measurable benefits for vulnerable populations

- Amplify youth voices in climate policy and advocacy processes at local and national levels

- Build a documented evidence base of youth-led climate interventions for wider replication and advocacy

- Foster peer learning and collaboration across youth organizations and initiatives in Yemen

3.  AVAILABLE FUNDING & GRANT STRUCTURE

| Pillar | Grants Available | Indicative Focus |
| --- | --- | --- |
| Pillar 1 — Capacity Building & Leadership Development | 1 grant ($500) | Training, mentorship, climate literacy, and skills-building for youth leaders |
| Pillar 2 — Community-Based Climate Initiatives ★ | 3 grants ($1,500) | Hands-on local climate action with direct, measurable community impact |
| Pillar 3 — Policy Advocacy & Movement Building | 1 grant ($500) | Youth-led advocacy campaigns, policy briefs, and coalition building |
| TOTAL | 5 grants ($2,500) | All grants equal at $500 per award — Yemen only |

★ Pillar 2 carries 3 of the 5 available grants given its potential for direct, measurable community impact and its centrality to AYSDN's reporting obligations to the Resource Partner Agency (RPA).

Important funding conditions:

- All grants are equal at $500 USD — partial awards will not be made

- Budgets must be denominated in USD and rounded to whole numbers

- The grant covers project implementation costs only — no overhead, salaries unrelated to the project, or institutional costs

- Disbursement will be made via mobile money (SabaFon, MTN Yemen) or bank transfer

4.  THEMATIC PILLARS & ELIGIBLE ACTIVITIES

Proposals must be submitted under one of the following three thematic pillars. Applicants must select the pillar that best describes the primary nature of their proposed project.

| Pillar 1 Capacity Building & Leadership Development | Pillar 2 Community-Based Climate Initiatives ★ Priority Pillar (3 grants) | Pillar 3 Policy Advocacy & Movement Building |
| --- | --- | --- |
| - Youth climate leadership workshops & peer-training - Mentorship with climate professionals - Climate literacy in schools & universities | - Solar lanterns, biogas micro-installations - Waste reduction & circular economy projects - Urban greening, tree planting & restoration - Water conservation & management - Climate-smart agriculture & food security pilots | - Youth advocacy campaigns (local & national) - Coalition building across organizations in Yemen - Youth-authored participatory research & policy briefs - Digital & media climate justice campaigns |

Ineligible activities (proposals including the following will be disqualified):

| - Scholarships or personal academic fees - Personal travel unrelated to the project - Political party activities or voter registration | - Salaries unrelated to the funded project - Purchase of expensive or durable equipment - Activities fully completed before the award date |
| --- | --- |

5.  ELIGIBILITY REQUIREMENTS

5.1  Individual Applicants

- Aged 18–35 years at the time of application

- Currently residing in Yemen

- Proposing a project aligned with one of the three thematic pillars

- Able to implement and complete the project within the grant period (Sep 2026 – Mar 2027)

- No prior AYSDN affiliation required

5.2  Youth-Led Organizations, Groups, NGOs, Initiatives & Platforms

- Group of 5–15 members, with a majority aged 18–35

- Must designate a lead contact who will sign the sub-grant agreement

- The organization or group must be based and operating in Yemen

- Project must fall within one of the three thematic pillars

- Able to complete all activities and submit a final report by March 15, 2027

Note: Sub-grants will not be made to formal registered institutions (INGOs, UN agencies, government bodies) without prior written approval from the Resource Partner Agency (RPA). Grantees must be individual youth or informal/formally registered youth-led entities.

6.  CFP TIMELINE & KEY DATES

| Phase | Dates | Description |
| --- | --- | --- |
| Launch & Publication of CFP | Jun 22–28, 2026 | CFP published via AYSDN website, social media, GIZ network, partner universities, and youth organization networks across Yemen |
| Proposal Submission Window | Jun 29 – Jul 28, 2026 | Applicants submit full proposal package online or by email. Clarification requests accepted until July 21, 2026 |
| Technical Review | Jul 29 – Aug 11, 2026 | 3-member AYSDN review panel evaluates all proposals against the published scoring rubric on a per-pillar basis |
| Selection & Notification | Aug 12–18, 2026 | Top-scoring proposals selected per pillar (1/3/1); all applicants notified; a 3-person waitlist maintained |
| Award & Disbursement | Aug 19–25, 2026 | Sub-grant agreements signed; $500 disbursed to each selected grantee via mobile money or bank transfer |
| Implementation & Support | Sep 2026 – Mar 2027 | Monthly group check-ins per pillar; peer exchange WhatsApp group; AYSDN technical support throughout |
| Final Reporting Deadline | March 15, 2027 | All grantees submit 1-page narrative report and receipts-based financial report to AYSDN |
| RPA Consolidation Report | Apr – Jun 2027 | AYSDN synthesizes all outcomes into the Final Report submitted to the Resource Partner Agency |

7.  PROPOSAL REQUIREMENTS & SUBMISSION PACKAGE

A complete proposal submission package must include all of the following components. Incomplete submissions will not be considered.

| # | Component | Requirements |
| --- | --- | --- |
| 1 | Completed Proposal Form | All sections of Part II of this document, filled in full. Download from aysdn.org/microgrants |
| 2 | Concept Note (2 pages max) | Describes the problem, proposed solution, activities, expected outcomes, and target beneficiaries. Arial/Calibri 11pt, single-spaced |
| 3 | Itemized Budget ($500 USD) | Line-by-line budget using the template in Part II Section C. Total must equal exactly $500 USD |
| 4 | Applicant Profile | Brief biography (individual) or group description including membership, experience, and operational location in Yemen |
| 5 | Signed Declaration | Completed and signed certification block in Part II Section F |

All submissions must be in English or Arabic. If submitting in Arabic, please include an English summary of the concept note (minimum 150 words). Submissions in other languages will not be reviewed.

How to Submit:

- Online portal:  aysdn.org/microgrants  (preferred)

- Email submission:  microgrants@aysdn.org  with subject line: "CFP YCJF-YEM-CFP-2026 — [Applicant Name] — [Pillar Number]"

- Clarification questions may be submitted to microgrants@aysdn.org by July 21, 2026. Responses will be shared with all applicants via the AYSDN website

8.  PROPOSAL EVALUATION & SELECTION

All eligible proposals will be reviewed by a 3-member AYSDN panel including at least one external youth leader. Each proposal is scored independently against the rubric below. The minimum qualifying score is 60 out of 100. Shortlisted applicants may be contacted for clarifications.

| Evaluation Criterion | Score | Evaluation Guidance |
| --- | --- | --- |
| Relevance to Pillar & YCJF Priorities | 25 | Proposal clearly addresses the chosen pillar and YCJF strategic goals |
| Feasibility within $500 & Timeline | 25 | Plan is achievable within 6 months and the $500 budget is realistic |
| Youth Leadership & Community Engagement | 20 | Genuine youth agency is central; target beneficiaries are engaged in design |
| Budget Clarity & Justification | 15 | All budget lines are itemized, specific, reasonable, and proportionate |
| Equity, Inclusion & Reach | 10 | Prioritizes underserved youth, women, persons with disabilities, or conflict-affected communities |
| Sustainability & Replicability | 5 | Impact continues post-grant or the model can be replicated elsewhere |
| TOTAL | 100 | Minimum qualifying score: 60 points |

Conflict of interest: Panel members must declare any relationship with applicants. Affected members will be recused from relevant reviews. Selection decisions are final and AYSDN is not obliged to provide individual feedback to unsuccessful applicants.

9.  GRANT MANAGEMENT, COMPLIANCE & REPORTING

9.1  Sub-Grant Agreements

- All selected grantees must sign a sub-grant agreement with AYSDN before disbursement

- The agreement sets out deliverables, reporting obligations, prohibited use clauses, and repayment conditions

- Grantees must maintain receipts for all expenditures and submit them at project close

9.2  Financial Controls

- All $500 disbursements tracked individually in AYSDN's accounting system

- Grantees must submit a receipts-based financial report at project completion

- Unspent funds must be returned to AYSDN; AYSDN will return uncommitted funds to the RPA

9.3  Prohibited Use & Compliance

- Funds may not be used for lobbying, political campaigning, voter registration, or personal benefit

- OFAC and anti-terrorism certifications collected from all grantees at agreement signing

- Anti-bribery declaration required as part of the sub-grant agreement

- Projects engaging children or vulnerable adults must submit a safeguarding plan for AYSDN review prior to disbursement

9.4  Reporting Requirements

- Mandatory 30-day milestone check-in with AYSDN program staff

- Monthly participation in group calls organized by pillar

- Final submission by March 15, 2027: 1-page narrative report + receipts-based financial report

- Grantees grant AYSDN permission to publish anonymized project summaries and success stories in the RPA Final Report

10.  GENERAL CONDITIONS

- AYSDN reserves the right to cancel or modify this CFP at any time without prior notice

- Submission of a proposal does not guarantee award of a grant

- AYSDN is not liable for any costs incurred in preparing or submitting proposals

- Successful applicants may be required to participate in a brief orientation session before disbursement

- AYSDN may reallocate up to 1 grant between pillars (within the 20% threshold) with director approval if a pillar receives insufficient qualifying applications

- Applicants who provide false or misleading information will be immediately disqualified and may be required to repay any disbursed funds

—.  CONTACT & FURTHER INFORMATION

| Online Portal | aysdn.org/microgrants |
| --- | --- |

| Email | microgrants@aysdn.org |
| --- | --- |

| Clarifications | Submit by July 21, 2026 — responses published on aysdn.org/microgrants |
| --- | --- |

| CFP Reference | YCJF-YEM-CFP-2026 |
| --- | --- |

| Deadline | July 28, 2026 at 23:59 Yemen Time (YT) |
| --- | --- |

AYSDN is committed to transparency, equity, and the empowerment of Yemeni youth. We strongly encourage applications from women, youth with disabilities, and applicants from underserved and conflict-affected governorates.

PART II PROPOSAL SUBMISSION FORM Youth Climate Justice Micro-Grant Program ¦ CFP Ref: YCJF-YEM-CFP-2026 Arab Youth Sustainable Development Network (AYSDN) ¦ $500 USD per grant ¦ Yemen ¦ Jun–Aug 2026

Instructions: Complete all sections below in full. Submit online at aysdn.org/microgrants or email to microgrants@aysdn.org by July 28, 2026. Attach your Concept Note (max 2 pages) and Budget as separate documents.

| A | APPLICANT INFORMATION |
| --- | --- |

A1.  Applicant Type

- Individual Youth (complete Section A2)

- Youth NGO / Group / Initiative / Platform (complete Section A3)

A2.  Individual Applicant Details

(Complete only if applying as an individual)

| Full Name Date of Birth (DD/MM/YYYY) |  |
| --- | --- |

A3.  Youth-Led Organization / Group / Initiative Details

(Complete only if applying as a group or organization)

Brief Description of Group

Who are you? How long have you been working together? What is your mandate?

Relevant Experience

Describe previous climate, community, or youth initiatives you have led or participated in.

| B | PROJECT PROPOSAL DETAILS |
| --- | --- |

B1.  Project Title

B2.  Project Location / Governorate in Yemen

Where will this project be implemented?

B3.  Thematic Pillar Selection

Select the single pillar that best describes the primary focus of your proposal:

- Pillar 1 — Capacity Building & Leadership Development

- Pillar 2 — Community-Based Climate Initiatives

- Pillar 3 — Policy Advocacy & Movement Building

B4.  Problem Statement

What specific climate or community problem does your proposal address? Why is it a priority in your context? (2–4 sentences)

B5.  Proposed Solution & Project Summary

In 4–6 sentences, describe your proposed project: what you will do, how, who will benefit, and what change you expect to create.

B6.  Project Activities & Approach

List the main activities in order. For each, briefly explain the methodology and who is responsible.

B7.  Target Beneficiaries

Who will directly benefit from this project? (e.g., rural youth, displaced families, school girls, farmers)

B8.  Expected Outcomes & Indicators

What will change as a result of your project? List 2–3 specific, measurable outcomes and how you will track them.

B9.  Project Implementation Timeline

Briefly outline key activities and milestones for each month of the implementation period (Sep 2026 – Mar 2027).

| Month | Proposed Activities / Milestones |
| --- | --- |
| September 2026 |  |
| October 2026 |  |
| November 2026 |  |
| December 2026 |  |
| January 2027 |  |
| February 2027 |  |
| March 2027 |  |

B10.  Risk Assessment & Mitigation

Identify at least two potential risks to project implementation (e.g., security, access, weather, coordination) and describe your mitigation approach for each.

| C | PROPOSED BUDGET ($500 USD) |
| --- | --- |

List how you plan to spend the full $500 grant. All budget lines must be clearly justified. The total must equal exactly $500 USD.

| Budget Item / Description |  | Amount (USD) | Qty / Unit | Justification / Notes |
| --- | --- | --- | --- | --- |
| TOTAL |  | $500.00 | — | Must equal exactly $500 USD |
| D | EQUITY, INCLUSION & REACH |  |  |  |

D1.  Does your proposal prioritize any of the following groups? (Select all that apply)

| - Women & girls - Displaced / refugee youth - Youth with disabilities | - Rural or remote communities - Youth from conflict-affected areas - Other (describe below) |
| --- | --- |

D2.  How does your proposal advance climate justice or equity?

D3.  How will your project reach or benefit marginalized communities?

| E | SUSTAINABILITY & SCALE |
| --- | --- |

E1.  How will the impact of your project continue after the grant ends?

E2.  Could this project be replicated in other communities or governorates? Describe how.

| F | CERTIFICATION & DECLARATION |
| --- | --- |

Applicant Certification & Declaration By submitting this proposal, the applicant(s) certify that: - All information in this proposal is truthful, accurate, and complete. - Grant funds will be used exclusively for the activities described in the proposal. - Funds will NOT be used for lobbying, political campaigning, voter registration, or private benefit. - I/we agree to comply with OFAC, anti-terrorism, and anti-bribery requirements in full. - Projects involving children or vulnerable adults will include a safeguarding plan for AYSDN review. - I/we will submit a final narrative report and financial accounting by March 15, 2027. - Any unspent funds will be returned to AYSDN promptly upon project completion.

| Lead Applicant / Authorized Signatory Title / Role Signature Date (DD / MM / YYYY) | Organization / Group Name Email Address Phone / WhatsApp (with country code) Governorate / Location in Yemen |
| --- | --- |

Submit your completed proposal at: aysdn.org/microgrants │ Email: microgrants@aysdn.org │ Deadline: July 28, 2026 │ CFP Ref: YCJF-YEM-CFP-2026